## Data
Formatted ID | Name | Project | Owner | Release | State | Description | Parent | Planned Start Date | Planned End Date | Preliminary Estimate | Refined Estimate | Leaf Story Plan Estimate Total | Leaf Story Count | Acceptance Criteria | Percent Done By Story Count
F-001 | Auth Feature 1 | Branch Transformation Initiative | Deepak Kumar | PI 05 | Closed | Enable auth capability tailored for B2B SaaS software commerce. | Auth Core Capabilities | 2026-01-01 | 2026-01-15 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0.98
F-002 | Catalog Feature 2 | Branch Transformation Initiative |  | PI 05 | Proposed | Enable catalog capability tailored for Subscription software commerce. | Catalog Core Capabilities | 2026-01-04 | 2026-01-18 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-003 | Payments Feature 3 | SME Banking Enablement | Suresh Singh | PI 05 | Proposed | Enable payments capability tailored for Marketplace software commerce. |  | 2026-01-07 | 2026-01-21 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-004 | Licensing Feature 4 | Mortgage Processing Optimization | Anthony Anderson | PI 05 |  | Enable licensing capability tailored for B2B SaaS software commerce. | Licensing Core Capabilities | 2026-01-10 | 2026-01-24 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-005 | Security Feature 5 | Real-Time Payments Engine | Rahul Kumar | PI 05 | Proposed | Enable security capability tailored for Subscription software commerce. | Security Core Capabilities | 2026-01-13 | 2026-01-27 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-006 | Admin Feature 6 | Card Fraud Detection Enhancement | Ashley Johnson | PI 05 | Proposed |  | Admin Core Capabilities | 2026-01-16 | 2026-01-30 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-007 | Analytics Feature 7 | Digital Savings Modernization | Vijay Kumar | PI 05 | Proposed | Enable analytics capability tailored for B2B SaaS software commerce. | Analytics Core Capabilities | 2026-01-19 | 2026-02-02 | 8 | 11 | 25 | 5 |  | 0
F-008 | Auth Feature 8 | Card Authorization Platform | Jessica Jackson | PI 05 | Proposed | Enable auth capability tailored for Subscription software commerce. | Auth Core Capabilities | 2026-01-22 | 2026-02-05 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-009 | Catalog Feature 9 | Tokenization Services Program | Suresh Reddy | PI 05 | Proposed | Enable catalog capability tailored for Marketplace software commerce. | Catalog Core Capabilities | 2026-01-25 | 2026-02-08 |  | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-010 | Payments Feature 10 | Tokenization Services Program | John Jackson | PI 05 | Proposed | Enable payments capability tailored for B2B SaaS software commerce. | Payments Core Capabilities | 2025-12-02 | 2026-02-11 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-011 | Licensing Feature 11 | Merchant Payments Hub | Divya Rao | PI 05 | Proposed | Enable licensing capability tailored for Subscription software commerce. | Licensing Core Capabilities | 2026-01-31 | 2026-02-14 | 8 |  | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-012 | Security Feature 12 | Payments Reconciliation Automation | Rachel Brown | PI 05 | Proposed | Enable security capability tailored for Marketplace software commerce. | Security Core Capabilities | 2026-02-03 | 2026-02-17 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-013 | Admin Feature 13 | Mortgage Processing Optimization | Divya Menon | PI 05 |  | Enable admin capability tailored for B2B SaaS software commerce. | Admin Core Capabilities | 2026-02-06 | 2026-02-20 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-014 | Analytics Feature 14 | Personal Banking Automation | Sarah Brown | PI 05 | Proposed | Enable analytics capability tailored for Subscription software commerce. | Analytics Core Capabilities | 2025-12-02 | 2026-02-23 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-015 | Auth Feature 15 | Customer Onboarding Acceleration | Pooja Reddy | PI 05 | Proposed | Enable auth capability tailored for Marketplace software commerce. | Auth Core Capabilities | 2026-02-12 | 2026-02-24 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-016 | Catalog Feature 16 | Instant Transfer Platform | Ashley Smith | PI 05 | Proposed | Enable catalog capability tailored for B2B SaaS software commerce. | Catalog Core Capabilities | 2026-02-15 | 2026-02-24 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-017 | Payments Feature 17 | Card Fraud Detection Enhancement | Sneha Patel | PI 05 | Proposed | Enable payments capability tailored for Subscription software commerce. | Payments Core Capabilities | 2026-02-18 | 2026-02-24 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-018 | Licensing Feature 18 | Customer Onboarding Acceleration | Amanda Smith | PI 05 | Proposed | Enable licensing capability tailored for Marketplace software commerce. | Licensing Core Capabilities | 2026-02-21 | 2026-02-24 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-019 | Security Feature 19 | Mortgage Processing Optimization | Anitha Iyer | PI 05 | Proposed | Enable security capability tailored for B2B SaaS software commerce. | Security Core Capabilities | 2026-02-24 | 2026-03-10 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-020 | Admin Feature 20 | Wealth Advisory Platform | Matthew Jackson | PI 06 | Proposed | Enable admin capability tailored for Subscription software commerce. | Admin Core Capabilities | 2026-02-27 | 2026-03-13 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-021 | Analytics Feature 21 | Loan Origination Enhancement | Karthik Patel | PI 06 | Proposed | Enable analytics capability tailored for Marketplace software commerce. | Analytics Core Capabilities | 2026-03-02 | 2026-03-16 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-022 | Auth Feature 22 | Digital Savings Modernization | Jennifer Johnson | PI 06 | Proposed | Enable auth capability tailored for B2B SaaS software commerce. | Auth Core Capabilities | 2026-03-05 | 2026-03-19 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-023 | Catalog Feature 23 | Merchant Payments Hub | Rahul Iyer | PI 06 | Proposed | Enable catalog capability tailored for Subscription software commerce. | Catalog Core Capabilities | 2026-03-08 | 2026-03-22 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-024 | Payments Feature 24 | Card Fraud Detection Enhancement | Lauren Martin | PI 06 | Proposed | Enable payments capability tailored for Marketplace software commerce. | Payments Core Capabilities | 2026-03-11 | 2026-03-25 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-025 | Licensing Feature 25 | Digital Savings Modernization | Lakshmi Reddy | PI 06 |  | Enable licensing capability tailored for B2B SaaS software commerce. | Licensing Core Capabilities | 2026-03-14 | 2026-03-28 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-026 | Security Feature 26 | Mortgage Processing Optimization | John Anderson | PI 06 | Proposed | Enable security capability tailored for Subscription software commerce. | Security Core Capabilities | 2026-03-17 | 2026-03-31 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-027 | Admin Feature 27 | Digital Wallet Integration | Divya Iyer | PI 06 | Proposed | Enable admin capability tailored for Marketplace software commerce. | Admin Core Capabilities | 2026-03-20 | 2026-04-03 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-028 | Analytics Feature 28 | Digital Wallet Integration | Sarah Thomas | PI 06 | Proposed | Enable analytics capability tailored for B2B SaaS software commerce. | Analytics Core Capabilities | 2026-03-23 | 2026-04-06 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-029 | Auth Feature 29 | Personal Banking Automation | Anitha Reddy | PI 06 | Proposed | Enable auth capability tailored for Subscription software commerce. | Auth Core Capabilities | 2026-03-26 | 2026-04-09 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-030 | Catalog Feature 30 | Cross-Border Payments Gateway | Rachel Martin | PI 06 | Proposed | Enable catalog capability tailored for Marketplace software commerce. | Catalog Core Capabilities | 2026-03-29 | 2026-04-12 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-031 | Payments Feature 31 | Mortgage Processing Optimization | Suresh Rao | PI 06 | Proposed | Enable payments capability tailored for B2B SaaS software commerce. | Payments Core Capabilities | 2026-04-01 | 2026-04-15 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-032 | Licensing Feature 32 | Customer Experience Revamp | James Thomas | PI 06 | Proposed | Enable licensing capability tailored for Subscription software commerce. | Licensing Core Capabilities | 2026-04-04 | 2026-04-18 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-033 | Security Feature 33 | Loan Origination Enhancement | Lakshmi Kumar | PI 06 | Proposed | Enable security capability tailored for Marketplace software commerce. | Security Core Capabilities | 2026-04-07 | 2026-04-21 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-034 | Admin Feature 34 | Contactless Payments Initiative | Matthew Harris | PI 06 | Proposed | Enable admin capability tailored for B2B SaaS software commerce. | Admin Core Capabilities | 2026-04-10 | 2026-04-24 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-035 | Analytics Feature 35 | Digital Savings Modernization | Divya Sharma | PI 06 | Proposed | Enable analytics capability tailored for Subscription software commerce. | Analytics Core Capabilities | 2026-04-13 | 2026-04-27 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-036 | Auth Feature 36 | Digital Wallet Integration | Megan Anderson | PI 06 | Proposed | Enable auth capability tailored for Marketplace software commerce. | Auth Core Capabilities | 2026-04-16 | 2026-04-30 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-037 | Catalog Feature 37 | Contactless Payments Initiative | Deepak Nair | PI 06 | Proposed | Enable catalog capability tailored for B2B SaaS software commerce. | Catalog Core Capabilities | 2026-04-19 | 2026-05-03 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-038 | Payments Feature 38 | Mortgage Processing Optimization | Daniel Taylor | PI 06 | Proposed | Enable payments capability tailored for Subscription software commerce. | Payments Core Capabilities | 2026-04-22 | 2026-05-06 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-039 | Licensing Feature 39 | Card Authorization Platform | Priya Sharma | PI 06 | Proposed | Enable licensing capability tailored for Marketplace software commerce. | Licensing Core Capabilities | 2026-04-25 | 2026-05-09 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-040 | Security Feature 40 | Instant Transfer Platform | Amanda Martin | PI 06 |  | Enable security capability tailored for B2B SaaS software commerce. | Security Core Capabilities | 2026-04-28 | 2026-05-12 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-041 | Admin Feature 41 | Digital Savings Modernization | Prakash Reddy | PI 06 | Proposed | Enable admin capability tailored for Subscription software commerce. | Admin Core Capabilities | 2026-05-01 | 2026-05-15 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-042 | Analytics Feature 42 | Contactless Payments Initiative | Michael Harris | PI 06 | Proposed | Enable analytics capability tailored for Marketplace software commerce. | Analytics Core Capabilities | 2026-05-04 | 2026-05-18 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-043 | Auth Feature 43 | Payments Reconciliation Automation | Deepak Singh | PI 06 | Proposed | Enable auth capability tailored for B2B SaaS software commerce. | Auth Core Capabilities | 2026-05-07 | 2026-05-19 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-044 | Catalog Feature 44 | Card Authorization Platform | Michael Smith | PI 06 | Proposed | Enable catalog capability tailored for Subscription software commerce. | Catalog Core Capabilities | 2026-05-10 | 2026-05-19 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-045 | Payments Feature 45 | Loan Origination Enhancement | Karthik Reddy | PI 06 | Proposed | Enable payments capability tailored for Marketplace software commerce. | Payments Core Capabilities | 2026-05-13 | 2026-05-19 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-046 | Licensing Feature 46 | Branch Transformation Initiative | Rachel Johnson | PI 06 | Proposed | Enable licensing capability tailored for B2B SaaS software commerce. | Licensing Core Capabilities | 2026-05-16 | 2026-05-19 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-047 | Security Feature 47 | Instant Transfer Platform | Anand Nair | PI 06 | Proposed | Enable security capability tailored for Subscription software commerce. | Security Core Capabilities | 2026-05-19 | 2026-06-02 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-048 | Admin Feature 48 | Retail Lending Platform | Daniel Brown | PI 07 | Proposed | Enable admin capability tailored for Marketplace software commerce. | Admin Core Capabilities | 2026-05-22 | 2026-06-05 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-049 | Analytics Feature 49 | Tokenization Services Program | Karthik Menon | PI 07 | Proposed | Enable analytics capability tailored for B2B SaaS software commerce. | Analytics Core Capabilities | 2026-05-25 | 2026-06-08 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-050 | Auth Feature 50 | Card Fraud Detection Enhancement | Robert Smith | PI 07 | Proposed | Enable auth capability tailored for Subscription software commerce. | Auth Core Capabilities | 2026-05-28 | 2026-06-11 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-051 | Catalog Feature 51 | Branch Transformation Initiative | Kavya Singh | PI 07 | Proposed | Enable catalog capability tailored for Marketplace software commerce. | Catalog Core Capabilities | 2026-05-31 | 2026-06-14 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-052 | Payments Feature 52 | Branch Transformation Initiative | Lauren Johnson | PI 07 | Proposed | Enable payments capability tailored for B2B SaaS software commerce. | Payments Core Capabilities | 2026-06-03 | 2026-06-17 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-053 | Licensing Feature 53 | SME Banking Enablement | Lakshmi Gupta | PI 07 | Proposed | Enable licensing capability tailored for Subscription software commerce. | Licensing Core Capabilities | 2026-06-06 | 2026-06-20 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-054 | Security Feature 54 | Mortgage Processing Optimization | William Thomas | PI 07 | Proposed | Enable security capability tailored for Marketplace software commerce. | Security Core Capabilities | 2026-06-09 | 2026-06-23 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-055 | Admin Feature 55 | Real-Time Payments Engine | Karthik Sharma | PI 07 | Proposed | Enable admin capability tailored for B2B SaaS software commerce. | Admin Core Capabilities | 2026-06-12 | 2026-06-26 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-056 | Analytics Feature 56 | Card Fraud Detection Enhancement | Michael Jackson | PI 07 | Proposed | Enable analytics capability tailored for Subscription software commerce. | Analytics Core Capabilities | 2026-06-15 | 2026-06-29 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-057 | Auth Feature 57 | Digital Savings Modernization | Deepak Iyer | PI 07 | Proposed | Enable auth capability tailored for Marketplace software commerce. | Auth Core Capabilities | 2026-06-18 | 2026-07-02 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-058 | Catalog Feature 58 | Card Authorization Platform | Christopher Thomas | PI 07 |  | Enable catalog capability tailored for B2B SaaS software commerce. | Catalog Core Capabilities | 2026-06-21 | 2026-07-05 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-059 | Payments Feature 59 | Tokenization Services Program | Kavya Reddy | PI 07 | Proposed | Enable payments capability tailored for Subscription software commerce. | Payments Core Capabilities | 2026-06-24 | 2026-07-08 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-060 | Licensing Feature 60 | Tokenization Services Program | Daniel Johnson | PI 07 | Proposed | Enable licensing capability tailored for Marketplace software commerce. | Licensing Core Capabilities | 2026-06-27 | 2026-07-11 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-061 | Security Feature 61 | Merchant Payments Hub | Aishwarya Sharma | PI 07 | Proposed | Enable security capability tailored for B2B SaaS software commerce. | Security Core Capabilities | 2026-06-30 | 2026-07-14 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-062 | Admin Feature 62 | Payments Reconciliation Automation | Sarah White | PI 07 | Proposed | Enable admin capability tailored for Subscription software commerce. | Admin Core Capabilities | 2026-07-03 | 2026-07-17 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-063 | Analytics Feature 63 | Mortgage Processing Optimization | Lakshmi Rao | PI 07 | Proposed | Enable analytics capability tailored for Marketplace software commerce. | Analytics Core Capabilities | 2026-07-06 | 2026-07-20 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-064 | Auth Feature 64 | Personal Banking Automation | Jessica Thomas | PI 07 | Proposed | Enable auth capability tailored for B2B SaaS software commerce. | Auth Core Capabilities | 2026-07-09 | 2026-07-23 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-065 | Catalog Feature 65 | Customer Onboarding Acceleration | Ramesh Rao | PI 07 | Proposed | Enable catalog capability tailored for Subscription software commerce. | Catalog Core Capabilities | 2026-07-12 | 2026-07-26 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-066 | Payments Feature 66 | Instant Transfer Platform | Daniel Martin | PI 07 |  | Enable payments capability tailored for Marketplace software commerce. | Payments Core Capabilities | 2026-07-15 | 2026-07-29 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-067 | Licensing Feature 67 | Card Fraud Detection Enhancement | Manoj Nair | PI 07 | Proposed | Enable licensing capability tailored for B2B SaaS software commerce. | Licensing Core Capabilities | 2026-07-18 | 2026-08-01 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-068 | Security Feature 68 | Customer Onboarding Acceleration | Jennifer Taylor | PI 07 | Proposed | Enable security capability tailored for Subscription software commerce. | Security Core Capabilities | 2026-07-21 | 2026-08-04 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-069 | Admin Feature 69 | Mortgage Processing Optimization | Vijay Sharma | PI 07 | Proposed | Enable admin capability tailored for Marketplace software commerce. | Admin Core Capabilities | 2026-07-24 | 2026-08-07 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-070 | Analytics Feature 70 | Wealth Advisory Platform | Sarah Martin | PI 07 | Proposed | Enable analytics capability tailored for B2B SaaS software commerce. | Analytics Core Capabilities | 2026-07-27 | 2026-08-10 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-071 | Auth Feature 71 | Loan Origination Enhancement | Arun Sharma | PI 07 | Proposed | Enable auth capability tailored for Subscription software commerce. | Auth Core Capabilities | 2026-07-30 | 2026-08-11 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-072 | Catalog Feature 72 | Digital Savings Modernization | Megan Thomas | PI 07 |  | Enable catalog capability tailored for Marketplace software commerce. | Catalog Core Capabilities | 2026-08-02 | 2026-08-11 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-073 | Payments Feature 73 | Merchant Payments Hub | Divya Gupta | PI 07 | Proposed | Enable payments capability tailored for B2B SaaS software commerce. | Payments Core Capabilities | 2026-08-05 | 2026-08-19 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-074 | Licensing Feature 74 | Card Fraud Detection Enhancement | David Johnson | PI 07 | Proposed | Enable licensing capability tailored for Subscription software commerce. | Licensing Core Capabilities | 2026-08-08 | 2026-08-11 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-075 | Security Feature 75 | Digital Savings Modernization | Pooja Sharma | PI 07 | Proposed | Enable security capability tailored for Marketplace software commerce. | Security Core Capabilities | 2026-08-11 | 2026-08-11 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0
F-076 | Admin Feature 76 | Mortgage Processing Optimization | Jessica Martin | PI 04 | Closed | Enable admin capability tailored for B2B SaaS software commerce. | Admin Core Capabilities | 2025-11-14 | 2025-11-28 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-077 | Analytics Feature 77 | Digital Wallet Integration | Sneha Rao | PI 04 | Closed | Enable analytics capability tailored for Subscription software commerce. | Analytics Core Capabilities | 2025-11-17 | 2025-11-30 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-078 | Auth Feature 78 | Digital Wallet Integration | Sarah Smith | PI 04 | In Progress | Enable auth capability tailored for Marketplace software commerce. | Auth Core Capabilities | 2025-11-20 | 2025-12-02 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-079 | Catalog Feature 79 | Personal Banking Automation | Divya Singh | PI 04 | Closed | Enable catalog capability tailored for B2B SaaS software commerce. | Catalog Core Capabilities | 2025-11-23 | 2025-12-02 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-080 | Payments Feature 80 | Cross-Border Payments Gateway | Amanda Brown | PI 04 | Closed | Enable payments capability tailored for Subscription software commerce. | Payments Core Capabilities | 2025-11-26 | 2025-12-02 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-081 | Licensing Feature 81 | Mortgage Processing Optimization | Neha Kumar | PI 04 |  | Enable licensing capability tailored for Marketplace software commerce. | Licensing Core Capabilities | 2025-11-29 | 2025-12-02 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-082 | Security Feature 82 | Customer Experience Revamp | Christopher Taylor | PI 04 | Closed | Enable security capability tailored for B2B SaaS software commerce. | Security Core Capabilities | 2025-09-01 | 2025-09-15 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-083 | Admin Feature 83 | Loan Origination Enhancement | Prakash Singh | PI 04 | Closed | Enable admin capability tailored for Subscription software commerce. | Admin Core Capabilities | 2025-09-04 | 2025-09-18 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-084 | Analytics Feature 84 | Contactless Payments Initiative | Rachel Anderson | PI 04 | Closed | Enable analytics capability tailored for Marketplace software commerce. | Analytics Core Capabilities | 2025-09-07 | 2025-09-21 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-085 | Auth Feature 85 | Digital Savings Modernization | Suresh Menon | PI 04 | In Progress | Enable auth capability tailored for B2B SaaS software commerce. | Auth Core Capabilities | 2025-09-10 | 2025-09-24 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-086 | Catalog Feature 86 | Digital Wallet Integration | John Smith | PI 04 | Closed | Enable catalog capability tailored for Subscription software commerce. | Catalog Core Capabilities | 2025-09-13 | 2025-09-27 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-087 | Payments Feature 87 | Contactless Payments Initiative | Aishwarya Reddy | PI 04 |  | Enable payments capability tailored for Marketplace software commerce. | Payments Core Capabilities | 2025-09-16 | 2025-09-30 | 5 | 8 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-088 | Licensing Feature 88 | Mortgage Processing Optimization | Jessica Harris | PI 04 | Closed | Enable licensing capability tailored for B2B SaaS software commerce. | Licensing Core Capabilities | 2025-09-19 | 2025-10-03 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-089 | Security Feature 89 | Card Authorization Platform | Neha Sharma | PI 04 | Closed | Enable security capability tailored for Subscription software commerce. | Security Core Capabilities | 2025-09-22 | 2025-10-06 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-090 | Admin Feature 90 | Instant Transfer Platform | William White | PI 04 | Closed | Enable admin capability tailored for Marketplace software commerce. | Admin Core Capabilities | 2025-09-25 | 2025-10-09 | 5 | 8 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-091 | Analytics Feature 91 | Digital Savings Modernization | Neha Menon | PI 04 | Closed | Enable analytics capability tailored for B2B SaaS software commerce. | Analytics Core Capabilities | 2025-09-28 | 2025-10-12 | 8 | 11 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-092 | Auth Feature 92 | Contactless Payments Initiative | Matthew Thomas | PI 04 | Closed | Enable auth capability tailored for Subscription software commerce. | Auth Core Capabilities | 2025-10-01 | 2025-10-15 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-093 | Catalog Feature 93 | Payments Reconciliation Automation | Ramesh Sharma | PI 04 | Closed | Enable catalog capability tailored for Marketplace software commerce. | Catalog Core Capabilities | 2025-10-04 | 2025-10-18 | 5 | 8 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-094 | Payments Feature 94 | Card Authorization Platform | Daniel Smith | PI 04 |  | Enable payments capability tailored for B2B SaaS software commerce. | Payments Core Capabilities | 2025-10-07 | 2025-10-21 | 8 | 11 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-095 | Licensing Feature 95 | Loan Origination Enhancement | Pooja Nair | PI 04 | Closed | Enable licensing capability tailored for Subscription software commerce. | Licensing Core Capabilities | 2025-10-10 | 2025-10-24 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-096 | Security Feature 96 | Branch Transformation Initiative | William Harris | PI 04 | Closed | Enable security capability tailored for Marketplace software commerce. | Security Core Capabilities | 2025-10-13 | 2025-10-27 | 5 | 8 | 20 | 4 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-097 | Admin Feature 97 | Instant Transfer Platform | Ramesh Gupta | PI 04 | Closed | Enable admin capability tailored for B2B SaaS software commerce. | Admin Core Capabilities | 2025-10-16 | 2025-10-30 | 8 | 11 | 25 | 5 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 1
F-098 | Analytics Feature 98 | Retail Lending Platform | Jennifer Anderson | PI 04 | In Progress | Enable analytics capability tailored for Subscription software commerce. | Analytics Core Capabilities | 2025-10-19 | 2025-11-02 | 8 | 11 | 30 | 6 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0.95
F-099 | Auth Feature 99 | Tokenization Services Program | Lakshmi Patel | PI 04 | Closed | Enable auth capability tailored for Marketplace software commerce. | Auth Core Capabilities | 2025-10-22 | 2025-11-03 | 5 | 8 | 35 | 7 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0.98
F-100 | Catalog Feature 100 | Card Fraud Detection Enhancement | Robert Jackson | PI 04 | Closed | Enable catalog capability tailored for B2B SaaS software commerce. | Catalog Core Capabilities | 2025-10-25 | 2025-11-08 | 8 | 11 | 15 | 3 | Given the feature is implemented, when a valid user performs the related action, then the system should complete it securely, accurately, and without errors. | 0.99