## Data
Gap ID | Work Item Type | Gap name | Corrective action | Gap type | Applicable to | Complexity
FE-01 | Feature | No description. | Add description. | Required field | Current and Past PI. | Low
FE-02 | Feature | No parent. | Add parent. | Required field | Current and Past PI. | Low
FE-03 | Feature | No acceptance criteria. | Add Acceptance Criteria in the Acceptance Criteria field. | Required field | Current and Past PI. | Low
FE-04 | Feature | No Preliminary Estimate. | Add Preliminary Estimate. | Required field | Current and Past PI. | Low
FE-05 | Feature | No Refined Estimate. | Add Refined Estimate. | Required field | Current and Past PI. | Low
FE-08 | Feature | Incorrect Planned start date. | Add correct Planned start date matching with PI start date. | Mismatching field | Current and Past PI. | Medium
FE-09 | Feature | Incorrect Planned end date. | Add correct Planned end date matching with PI end date. | Mismatching field | Current and Past PI. | Medium
FE-06 | Feature | No Owner. | Add Owner. | Required field | Current and Past PI. | Low
FE-07 | Feature | No State. | Add State. | Required field | Current and Past PI. | Low
FE-10 | Feature | Incorrect State for past PI feature. | Change the State of the feature as Closed, because the PI of the feature is in the past. | Mismatching field | Past PI only. | High
FE-11 | Feature | Incorrect Percent done for past PI Feature. < 100% | Change the State of child stories as Accepted. | Mismatching field | Past PI only. | High
FE-12 | Feature | Incorrect State for 100% done Feature. | Change the State as Closed. | Mismatching field | Current PI only. | High
FE-13 | Feature | Incorrect State. State is Closed but Percent done is < 100%. . | Change the State of child stories as Accepted. Or Change the State of Feature as In-progress. | Mismatching field | Current PI only. | High
US-01 | User Story | No description. | Add description. | Required field | Current and Past Iteration. | Low
US-02 | User Story | No parent / Feature. | Add parent / Feature. | Required field | Current and Past Iteration. | Low
US-12 | User Story | Incorrect Parent. | Match the PI of User Story with PI of Parent Feature. | Mismatching field | Current and Past Iteration. | High
US-03 | User Story | No acceptance criteria. | Add Acceptance Criteria in the Acceptance Criteria field. | Required field | Current and Past Iteration. | Low
US-04 | User Story | No Plan Estimate. | Add Plan Estimate. | Required field | Current and Past Iteration. | Low
US-09 | User Story | Incorrect Plan Estimate. | Add correct Plan Estimate (1, 2, 3, 5 or 8). | Mismatching field | Current and Past Iteration. | High
US-10 | User Story | Incorrect Schedule State. | Update the Schedule State as Accepted. | Mismatching field | Past Iteration only. | Medium
US-05 | User Story | No Task Estimate. | Add Task Estimate. User Story is in past iteration. | Required field | Past Iteration only. | Low
US-06 | User Story | No Actuals. | Add Task Actuals. User Story is in past iteration. | Required field | Past Iteration only. | Low
US-13 | User Story | Plan Estimate and Task Estimate do not match. | Match Plan Estimate with Task Estimate in future User Stories. | Mismatching field | Past Iteration only. | High
US-07 | User Story | No PI / Release. | Add PI / Release. | Required field | Current and Past Iteration. | Low
US-11 | User Story | PI / Release does not match with Iteration. | Match PI / Release with Iteration. | Mismatching field | Current and Past Iteration. | Medium
US-08 | User Story | No Owner. | Add Owner. | Required field | Current and Past Iteration. | Low